## Gantt Chart - 9 Weeks
Task Name | Start Week | Duration (Weeks) | End Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Authentication | 1 | 2 | 2
Lead Management | 3 | 2 | 4
Dashboard | 5 | 1 | 5
Team Leader | 6 | 1 | 6
Logs & Notifications System | 7 | 1 | 7
Testing | 8 | 2 | 9