## CRM Roadmap
SMART CRM PROJECT ROADMAP (10 WEEKS)
Phase | Owner | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Planning & Requirements | Team | 1 | 1
ERD & System Design | Backend | 1 | 2
Authentication APIs | Backend | 2 | 3
User & Role Management | Backend | 3 | 4
CRM Lead Module | Backend | 4 | 5
Task Management System | Backend | 5 | 6
Dashboard Analytics | Frontend | 6 | 7
Frontend UI Development | Frontend | 6 | 8
API Integration | Frontend | 7 | 8
Testing & Bug Fixing | QA | 9 & 10 | 9 & 10
this is for bunian
https://github.com/EzzzzAldin/todo-debug-task-Reactjs/compare/master...OmarMahmoud22:todo-debug-task-Reactjs:yazen?expand=1
this is for section
https://github.com/tarekelkanaria/d-care